## Sheet1
Risk Register AGC
Prepared by: Soulivong Phimmathong | [8 empty] | Date: 21 May 2016
No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
R1 | 1 | misunderstanding requirements | some requirement might not be able to explain verbally or members might not know the exact requirement for the project | People risk | poor communication and analysis the requirement | members realize that they do not understand the requirements | Set up a meeting with customer to clarify their expectations and write a clear conscise SRS | Project Manager | high | high | Completed
R2 | 2 | unclear target market | There are many kind of restaurants and many kind of customers out there in Hanoi those might lead to focusing on the wrong group of customers | Market risk | ambiguous business needs | customers realize that they are not sure whether the services is suitable for them or not | set up a meeting with customer to clarify their expectations and write a clear concise SRS | SRS Leader | medium | medium | Researching
R3 | 3 | unachievable requirement | many technologies and techniques are new to all members. Member might found that those requirements are too difficult for him/her | Structure/Process risk | never been doing before and cannot find solution on the internet | members realize that they cannot solve the problems themselves and cannot find on the internet | ask expert or modify the requirement but must be accepted by the team or customers | ALL | low | medium | Not yet implement
R4 | 4 | conflict among members | individual might not get along with one another by any reasons that will cause working inefficiency | People risk | different opinion, or unsatisfactory habits | members strongly disagree with one another opinion or they don't feel like want to work with each other | separate work tasks and/or use moderator to mediate | Project Manager and/or Advisor | high | medium | Managing
R5 | 5 | lack of attention form member's business | members have another work or activities to do apart from AGC project, they might lose focusing on the project | People risk | too many workload | members realize that they have to do too may work with time limited | assign tasks to the right and suitable members | Project Manager | medium | medium | Managing
R6 | 6 | over the deadline | members cannot finish tasks assigned on time | People risk | lack of attention | members feel they can procrastinate | remind and/or add more resources | Project Manager | medium | medium | Managing
R7 | 7 | unknown process | Mr. PM is new and might not what processes should be involved and what should not | Structure/Process risk | lack of experience | unexpected needed work occur and/or should not occur | Check if the processes occurred are crucial or not then find proper solutions | Advisor | low | medium | Analyzing process
R8 | 8 | lack of fund | We might not have enough money to research the market and to communicate with customers | Financial risk | high cost marketing research and communication | we realize that we have money less than we suppose to have | ask for share capital | Advisor | low | medium | Not yet occurred
R9 | 9 | overused of informal communication tool | Use too much social media tool such as Facebook, Skype without document informations in a proper standard way might cause data review and analysis issues | Technology risk | familiarity and laziness | work is not recorded is a proper way | redocument the documentation and fit it into the official documentation format | ALL | low | low | Encoraging members to use official tool
R10 | 10 | insufficient hardware test devices | We need many devices to test if the website works and displays properly in different kind of devices | Technology risk | have only general devices | need to test on special and specific devices | Using emulator or contact to the needed hardware shops for borrowing | Test Leader | high | low | Will be implementingduring the testing phase